## Roadmap Summary
Stage | IBM Effort (hours) | Client Effort (hours) | Condition
Stage ⓪ — Curriculum-Alignment Workshop Totals | 24 | 36
Stage ① — Curriculum-Alignment Indicators Study Totals | 74 | 36 | Heavy IBM Assist
Stage ① — Curriculum-Alignment Indicators Study Totals | 58 | 90 | Client DIY
Stage ②ⓐ — Develop Interface to Unprecedented Third-Party Source | 69 | 34 | Lower-bound IBM-effort scenario: ⧐ Simple structure to third-party extract. ⧐ Learning-standards cross-mapping by text-string manipulation.
Stage ②ⓐ — Develop Interface to Unprecedented Third-Party Source | 80 | 34 | Upper-bound IBM-effort scenario: ⧐ Complex structure to third-party extract. ⧐ Learning-standards cross-mapping by curriculum-management tool.
Stage ②ⓑ — Develop Interface to Precedented Third-Party Source | 55 | 27 | Lower-bound IBM-effort scenario: ⧐ Learning-standards cross-mapping by text-string manipulation.
Stage ②ⓑ — Develop Interface to Precedented Third-Party Source | 58 | 27 | Upper-bound IBM-effort scenario: ⧐ Learning-standards cross-mapping by text-string manipulation.
Stage ②ⓒ — Digitize Curriculum Totals | 30.5 | 24.5

## Stage ⓪ — Curric-Survey WrkShop
Task | IBM Effort (hours) | Client Effort (hours) | Estimation Bases | Delivery Assets
Stage ⓪ — Curriculum-Alignment Workshop Totals | 24 | 36
⓪.1 Inventory curriculum, assessments artifacts. | 2 | 18
⓪.1.1 Provide, explain patterns. | 1 | 3
⓪.1.2 Collect, collate curriculum maps. |  | 6 | Will be highly variable, depending on state of client practrices.
⓪.1.3 Provide, explain patterns for standards-aligned evidence of learning employed by Watson. | 1 | 2
⓪.1.4 Extract from assessment-data system exemplary standards-aligned evidence of learning.. |  | 4 | Client Effort: 2 hours/source system × 2 source systems 4 hours
⓪.1.5 Assemble assessment calendars, learning-standards baselines, learning-standards vertical alignments (if applicable). |  | 3
⓪.2 Perform alignment analysis. | 10 | 6
⓪.2.1 Visually audit curriculum artifacts assembled during ⓪.1. | 8
⓪.2.2 Engage in dialogue to clarify curriculum artifacts. | 2 | 6 | IBM Effort: 1 hr/Q&A session × 2 Q&A sessions 2 hours Client Effort: 1 hr/Q&A session/participant × 2 Q&A sessions × 3 participants 6 hours
⓪.3 Conduct curriculum-alignment review workshop. | 4 | 12 | IBM Effort: 4 hrs/workshop × 1 workshop 4 hours Client Effort: 4 hrs/workshop/participant × 1 workshop × 3 participants 12 hours | ⧐ Curriculum-Alignment Triage Tool (to be developed).
⓪.4 Prepare, deliver final report. | 9 | 3
⓪.4.1 Prepare final report. | 8
⓪.4.2 Conduct final review. | 1 | 3 | IBM Effort: 1hr/review × 1 review 1 hour Client Effort: 1 hr/final review/participant × 1 final review × 3 participants 3 hours

## Stage ① — Curric-Algmt Study
| Heavy IBM Assist |  | Client DIY
Task | IBM Effort (hours) | Client Effort (hours) | IBM Effort (hours) | Client Effort (hours) | Estimation Bases | Delivery Assets
Stage ① — Curriculum-Alignment Indicators Study Totals | 74 | 36 | 58 | 90
①.1 Configure sftp for secure data sharing | 2 |  | 2
①.2 Digitize Curriculum | 6 | 4 | 0 | 14 |  | ⧐ Curriculum-Management Tool
①.2.1 Configure Curric-Mgt Tool | 2 |  |  | 2
①.2.2 Digitize four course blueprints
①.2.2.1 Collect, colate blueprints |  | 4 |  | 4
①.2.2.2 Enter blueprints into Curric-mgt tool | 4 |  |  | 8 | IBM: 1 hour/blueprint × 4 blueprints using cirric-mgt tool Client: 2 hours/blueprint × 4 blueprints using cirric-mgt tool
①.3 Perform data preparation | 22 | 18 | 12 | 62
①.3.1 Provide enrollment data for in-scope courses. |  | 6 |  | 6 | Client: 6 hours to get data out of SIS
①.3.2 Extract assessments data for in-scope courses. |  | 4 |  | 4 | Client: 4 hours/assessments source × one source
①.3.3 Reshape, transform assessments data | 12 | 2 | 8 | 24 | Client DIY: ⧐ 24 hours to reshape extract from single source ⧐ IBM consult, validate ≲ 8 hours for single source. IBM Assist: ⧐ 12 hours to reshape, transform extract from single source. ⧐ Client explains structure of extract, reviews for validity.
①.3.4 Build cross-walk between learning-standards code for source system → Watson | 8 | 2 | 2 | 24 | Client DIY: ⧐ (125 stds/blueprint ÷ 20 stds/hr/source) × 1 source × 4 blueprints ≈ 24 hours using curric-mgt tool ⧐ IBM consult, validate ≲ 2 hours for single source. IBM Assist: ⧐ 8 hours using text-string manipulation (e.g., python). ⧐ Client 2 hours to validate. | ⧐ Curriculum-Management Tool - Crosswalk Utility
①.3.5 Review learning-standard progressions. | 2 | 4 | 2 | 4 | Key Assumption: Based on existing Watson-Conforming progression set. IBM: 2 hours to produce and explain. Client: 4 hours to review and understand.
①.4 Perform Curriculum-Alignment analysis | 26 | 0 | 26 | 0
①.4.1 Produce alignment indicators for course-blueprint ⟷ learning-standard progressions | 6 |  | 6 |  |  | ⧐ Curriculum-Alignment Indicators: Course-blueprint alignment to learning-standard progressions
①.4.2 Produce alignment indicators for course-blueprint ⟷ evidence of learning | 6 |  | 6 |  |  | ⧐ Curriculum-Alignment Indicators: Assessments coverage of course blueprints
①.4.3 Perform evidentiary-coverage analysis | 6 |  | 6 |  |  | ⧐ Curriculum-Alignment Indicators: Evidentiary/estimation coverage of learning standards
①.5 Develop detailed implementation plan with estimates | 8 |  | 8
①.6 Develop and deliver final report | 10 | 10 | 10 | 10
①.6.1 Develop final report | 8 |  | 8
①.6.2 Deliver final report | 2 | 8 | 2 | 8 | IBM Effort. 2 hours/final-review session × 1 final-review session 2 hours Client Effort. 2 hours/final-review session/participant × 1 final-review session × 4 participants 8 hours
①.6.3 Review and accept final report |  | 2 |  | 2
①.7 Administer task | 8 | 4 | 8 | 4

## Stage ②ⓐ — Unpreced Source
| Lower Bound |  | Upper Bound
Task | IBM Effort (hours) | Client Effort (hours) | IBM Effort (hours) | Client Effort (hours) | Estimation Bases | Delivery Assets
Stage ②ⓐ — Develop Interface to Unprecedented Third-Party Source | 69 | 34 | 80 | 34
②ⓐ.1 Reshape and transform export from third-party system | 14 | 7 | 22 | 7
②ⓐ.1.1 Audit operationally-representative third-party extract | 2 | 2 | 2 | 2
②ⓐ.1.2 Develop attribute-by-attrubute source-to-target mapping | 3 | 3 | 3 | 3
②ⓐ.1.3 Develop logic to reshape (if necessary), transform third-party extract. | 8 |  | 16 |  | Upper-bound IBM Effort: Third-part extract comes single, long-format table. Lower-bound IBM Effort: Third-part extract comes in multiple, wide-format tables.
②ⓐ.1.4 Audit Watson-conforming transform from third-party extract. | 1 | 2 | 1 | 2
②ⓐ.2 Align third-party learning-standard codes to Watson codes. | 7 | 2 | 10 | 2 |  | ⧐ Curriculum-Management Tool - Crosswalk Utility
②ⓐ.2.1 Develop cross-walk learning-standard codes used by third-party and Watson. | 6 |  | 9 |  | Upper-bound IBM Effort: Use curriculum-management tool. (125 standards/blueprint ÷60 standards/hour) × 4 blueprints 9 hours Lower-bound IBM Effort: Develop text-string logic to map between learning-standard notations. 6 hours
②ⓐ.2.2 Audit learning-standard cross-walk. | 1 | 2 | 1 | 2
②ⓐ.3 Prepare School District to become self-sufficient. | 7 | 3 | 7 | 3 |  | ⧐ Curriculum-Management Tool ⧐ Curriculum-Management Tool - Crosswalk Utility
②ⓐ.2.1 Configure curriculum-management tool. | 4 |  | 4
②ⓐ.2.2 Administer training in curriculum-management tool. | 3 | 3 | 3 | 3 | IBM Effort: 1 hours/session × 1 training session 1 hours Additional post-training ad-hoc support: 2 hours. Client Effort: 1 hours/session/participant × 3 participants/session × 1 training session 3 hours
②ⓐ.4 Deploy, Integrate, Test interface to third-party system. | 41 | 22 | 41 | 22
②ⓐ.4.1 Define system workflow. | 4 | 4 | 4 | 4 | IBM Effort. Integrate data-conversion logic with Watson-Education Data-Interface (WEDI) logic: 32 hours.
②ⓐ.4.2 Integrate data-conversion logic from ②ⓐ.1 according to workflow. | 32 | 12 | 32 | 12 | Client Effort. Develop repeatable (automated?) procedure to get axtract according to system workflow: 12 hours IBM Effort. Integrate third-party-conversion logic into Watson Education Data Interface (WEDI): 32 hours.
②ⓐ.4.3 Conduct end-to-end-test. | 4 | 4 | 4 | 4
②ⓐ.4.4 Administer training in problem-reporting tool (Salesforce). | 1 | 2 | 1 | 2

## Stage ②ⓑ — Preced Source
| Lower Bound |  | Upper Bound
Task | IBM Effort (hours) | Client Effort (hours) | IBM Effort (hours) | Client Effort (hours) | Estimation Bases | Delivery Assets
Stage ②ⓑ — Develop Interface to Precedented Third-Party Source | 55 | 27 | 58 | 27
②ⓑ.1 Align third-party learning-standard codes to Watson codes. | 7 | 2 | 10 | 2 |  | ⧐ Curriculum-Management Tool - Crosswalk Utility
②ⓑ.1.1 Develop cross-walk learning-standard codes used by third-party and Watson. | 6 |  | 9 |  | Upper-bound IBM Effort: Use curriculum-management tool. (125 standards/blueprint ÷60 standards/hour) × 4 blueprints 9 hours Lower-bound IBM Effort: Develop text-string logic to map between learning-standard notations. 6 hours
②ⓑ.1.2 Audit learning-standard cross-walk. | 1 | 2 | 1 | 2
②ⓑ.2 Prepare School District to become self-sufficient. | 7 | 3 | 7 | 3 |  | ⧐ Curriculum-Management Tool ⧐ Curriculum-Management Tool - Crosswalk Utility
②ⓑ.2.1 Configure curriculum-management tool. | 4 |  | 4
②ⓑ.2.2 Administer training in curriculum-management tool. | 3 | 3 | 3 | 3 | IBM Effort: 1 hours/session × 1 training session 1 hours Additional post-training ad-hoc support: 2 hours. Client Effort: 1 hours/session/participant × 3 participants/session × 1 training session 3 hours
②ⓑ.3 Deploy, Integrate, Test interface to third-party system. | 41 | 22 | 41 | 22
②ⓑ.3.1 Define system workflow. | 4 | 4 | 4 | 4 | IBM Effort. Integrate data-conversion logic with Watson-Education Data-Interface (WEDI) logic: 32 hours.
②ⓑ.3.2 Integrate data-conversion logic from ②ⓑ.1 according to workflow. | 32 | 12 | 32 | 12 | Client Effort. Develop repeatable (automated?) procedure to get axtract according to system workflow: 12 hours IBM Effort. Integrate third-party-conversion logic into Watson Education Data Interface (WEDI): 32 hours.
②ⓑ.3.3 Conduct end-to-end-test. | 4 | 4 | 4 | 4
②ⓑ.3.4 Administer training in problem-reporting tool (Salesforce). | 1 | 2 | 1 | 2

## Stage ②ⓒ — Digitize Curric
Task | IBM Effort (hours) | Client Effort (hours) | Estimation Bases | Delivery Assets
Stage ②ⓒ — Digitize Curriculum Totals | 30.5 | 24.5
②ⓒ.1 Produce digitized curriculum artifacts | 17 | 16 | Key Assumption: Artifacts from Stage ⓪ — or derivatives thereof — are collated and represent inputs to this work.
②ⓒ.1.1 Digitize curriculum maps. | 9 | 2 | Assumption: IBMer employs curriculum-mgt tool. IBM Effort: (125 standards/blueprint ÷60 standards/hour) × 4 blueprints 9 hours Client Effort: Visually validate results. 30 minutes/blueprint × 4 blueprints 2 hours | ⧐ Curriculum-Management Tool ⧐ Curriculum-Management Tool - Crosswalk Utility
②ⓒ.1.2 Digitze course catalog, cross-map to blueprints. | 4 | 6 | Assumption: IBMer performs ad-hoc data-wrangling. Client Effort. Extract course-catalog from SIS: 4 hours Review blueprint⟷course-catalog cross-walk: 2 hours IBM Effort. Wrangle course catalogue into Wastson-conforming format: 2 hours Cross-map course-catalog to blueprints: 2 hours | ⧐ Curriculum-Management Tool
②ⓒ.1.3 Extract Watson-conforming digitized learning-standards baseline. | 2 | 4 | IBM Effort. Extract digitized learning standards from staging database: 2 hours. Client Effort. Review and understand digitized learning standards: 4 hours.
②ⓒ.1.4 Extract Watson-conforming learning-standards progressions. | 2 | 4 | IBM Effort. Extract digitized learning-standard progressions from staging database: 2 hours. Client Effort. Review and understand digitized learning-standard progressions: 4 hours.
②ⓒ.2 Prepare client to become self-sufficient in managing digitized curriculum. | 13.5 | 8.5
②ⓒ.2.1 Configure curriculum-management tool. | 4 |  | IBM Effort: 4 hours
②ⓒ.2.2 Administer training in curriculum-management tool. | 3.5 | 4.5 | IBM Effort: 1½ hours/session × 1 training session 1½ hours Additional post-training ad-hoc support: 2 hours. Client Effort: 1½ hours/session/participant × 3 participants/session × 1 training session 4½ hours
②ⓒ.2.3 Perform, explain alignment analysis. | 6 | 4 | IBM Effort. Conduct alignment analysis and package results: 4 hours Explain results: 2 hours Client Effort. Review Alignment Analysis: 4 hours.